## AutomationROKS
IBM Consulting Autmation Essentials - Onboarding checklist
Phase | Task | Status | Owner | Reviewer | Notes
PRE-DEV | Onboarding template filled | Done | Onboarding Architect | OA
PRE-DEV | CICD team created | Done | Support Team | OA
PRE-DEV | Namespace created | In Progress | Essentials SRE | OA
PRE-DEV | Infrastructure size agreed | Done | Solution, OA, SRE | SRE | for instance DB size should be agreed at least for DEV and QA at that point
PRE-DEV | Infrastructure created | In Progress | SRE | SRE, Solution
PRE-DEV | Components imported in CICD | In Progress | Solution | OA
PRE-DEV | Piplelines created in CICD | Done | Solution | OA | SRE will help with the tokens for connecting to the namespace
PRE-DEV | Helm Chart Draft | Done | Solution | OA
DEV | Deployment in the Namespace | TBD | Solution | OA
DEV | Specific IN/OUT connections | TBD | Solution, SRE | SRE
DEV | Specific in-cluster dependencies | TBD | Solution, SRE | OA
DEV | Ingresses for exposed components | TBD | Solution | OA
DEV | Helm Chart Final | TBD | Solution | OA
DEV | Fully functional App in Namespace | TBD | Solution | Solution, OA
DEV | Catalog Tile | In Progress | Solution, OA | Solution, OA
DEV | Create Teams and add Users/Roles TBD | TBD | Solution | OA
DEV | Security Scan - Initial | TBD | Mihai | Security Consultant, OA | Static scan; component scan, PI treatment in transit and at rest
DEV | Auth and Autorization via Ingress and security lib; Use of platform's roles | TBD | Solution | OA
DEV | Audit for the main entry points | TBD | Solution | OA
DEV | UI Shell - menu and privacy | TBD | Solution | OA | for UI components
DEV | Data Loader triggered in Helm chart | Done | Solution | OA, SRE
DEV | Multitenancy implementation | TBD | Solution | OA
DEV | Settings, Properties, Catalog Actions | TBD | Solution | OA
DEV | Metrics | TBD | Solution | OA
DEV | Other Fwks: Logging, Notifications, Settings, Email Templates | TBD | Solution | OA
DEV | UX review intiated | Done | Solution, UX | UX
DEV | Zero Touch Installation done | TBD | Solution, OA | OA
DEV | Volumetrics for UAT | TBD | Solution, OA | OA
DEV | Connectivity review for UAT; Fwd proxy |  | Solution, SRE | OA, SRE | add Fwd proxy code if needed
DEV | Backup and data retention strategy for UAT & PROD | TBD | Solution, SRE, OA | SRE, OA
UAT | Environment Creation (ns + middleware) | TBD | SRE | SRE
UAT | Tile/Team/Users/Roles creation | TBD | SRE, Solution | SRE, Solution
UAT | CICD stages for UAT | TBD | Solution | OA | SRE will help with the tokens for connecting to the namespace
UAT | Deployment via Helm chart | TBD | SRE | SRE, Solution
UAT | Security sign-off | TBD | Mihai | Security Consultant, OA
UAT | UAT sign-off | TBD | Solution | Solution
UAT | Tracing: Jaeger testing for all components | TBD | Solution | SRE, OA
UAT | Application monitoring for all components | TBD | Solution | SRE, OA
UAT | Data Backup tests | TBD | SRE, Solution | Solution, OA
PERF | Environment Creation (ns + middleware) | TBD | SRE | SRE
PERF | Tile/Team/Users/Roles creation | TBD | SRE, Solution | SRE, Solution
PERF | CICD stages for PERF | TBD | Solution | OA | SRE will help with the tokens for connecting to the namespace
PERF | Deployment via Helm chart | TBD | SRE | SRE, Solution
PERF | Security sign-off | TBD | Mihai | Security Consultant, OA
PERF | Application monitoring for all components | TBD | Solution | SRE, OA
PERF | Tracing: Jaeger testing for all components | TBD | Solution | SRE, OA
PERF | PERF sign-off | TBD | Solution | Solution
PERF | Volumetrics for PROD | TBD | Solution, OA | OA
PROD | …