## Sheet1
Task Name | Sub Task | Task Details | Owner | ROM (Man Hour) | Planned Start | Actual Start | Planned End | Actual End | Dependecies | Status | Remarks
ROKS Provisioning
| Provision ROKS Cluster |  |  |  | 2021-10-27 | 2021-10-27 | 2021-10-27 | 2021-10-27
| Providing Access to Stakeholders |  |  |  | 2021-10-27 | 2021-10-27 | 2021-10-29
Installing Essentials
| Installing Essentials on ROKS |  |  |  | 2021-10-29 | 2021-10-29 | 2021-11-01
| Essetials Data Migration |  |  |  | 2021-11-01 |  | 2021-11-03
| Test Essentials |  |  |  | 2021-11-03 |  | 2021-11-05
Installing Pipeline
| Installing Pipeline |  |  |  | 2021-11-05 |  | 2021-11-06
| Test Pipeline |  |  |  | 2021-11-06 |  | 2021-11-06
| Delete Test Pipeline Deployment |  |  |  | 2021-11-06 |  | 2021-11-07
Installing 3rd Party Services (for all namespaces)
(it is expected that all solutions will be coming in UAT from Dev) | Installing MySQL and Testing (if needed)
(So all 3rd party services should be replicated from Dev to UAT) | Installing Mongo and Testing (if needed)
Installing RabbitMQ and Testing (if needed)
Installing PostgreSQL and Testing (if needed)
Installing Redis and Testing (if needed)
Installing Camunda and Testing (if needed)
Provisioning Ancillary Services from Cloud (TBD)
Provisioning Watson Services (NLC/NLU)
Provisioning FaaS
Provisioning WDS
Installing EFK
Add worker node for EFK
Install EFK
Add RBAC and Test EFK
Configuring Firewall
Apply Rule on Vyatta
Testing Vyatta
Installing Prometheus Stack
Install Grafana
Connect ROKS's default Prometheus to Grafana
Configure AlertManager
Test end to end
Install Service Mesh
Install Elasticsearch
Install Jaeger
Install Kiali
Install Service Mesh
Deploy Solutions Through Pipelines
(One Test Soln will be configure to deploy in UAT) | Configure Stage in Pipeline for UAT |  | SRE / Soln Team
(Same Test Soln will be tested in UAT) | Deploy Soln in UAT |  | SRE / Soln Team
| Test Soln in UAT |  | SRE / Soln Team
Setup Access for Soln Teams
Setup Developer/Deployer Access