## Sheet1
Task Name | Sub Task | Task Details | Owner | ROM (Man Hour) | Planned Start | Actual Start | Planned End | Actual End | Dependecies | Status | Remarks
ROKS Provisioning
| Provision ROKS Cluster |  |  |  | 2021-10-27 | 2021-10-27 | 2021-10-27 | 2021-10-27
| Providing Access to Stakeholders |  |  |  | 2021-10-27 | 2021-10-27 | 2021-10-29
Installing Essentials
| Installing Essentials on ROKS |  |  |  | 2021-10-29 | 2021-10-29 | 2021-11-01 | 2021-11-03
| Essetials Data Migration |  |  |  | 2021-11-11 |  | 2021-11-12
| Test Essentials |  |  |  | 2021-11-11 | 2021-10-29 | 2021-11-15 | 2021-11-19
Installing Pipeline
| Installing Pipeline |  |  |  | 2021-11-12 |  | 2021-11-12
| Test Pipeline |  |  |  | 2021-11-12 |  | 2021-11-15
| Delete Test Pipeline Deployment |  |  |  | 2021-11-12 |  | 2021-11-15
Installing 3rd Party Services (for all namespaces)
(it is expected that all solutions will be coming in UAT from Dev) | Installing MySQL and Testing (if needed) |  |  |  | 2021-11-11 | 2021-11-11 | 2021-11-11 | 2021-11-15
(So all 3rd party services should be replicated from Dev to UAT) | Installing Mongo and Testing (if needed) |  |  |  | 2021-11-11 | 2021-11-11 | 2021-11-11 | 2021-11-15
| Installing RabbitMQ and Testing (if needed) |  |  |  | 2021-11-11 | 2021-11-11 | 2021-11-11 | 2021-11-15
| Installing PostgreSQL and Testing (if needed) |  |  |  | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-15
| Installing Redis and Testing (if needed) |  |  |  | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-15
| Installing Camunda and Testing (if needed) |  |  |  | 2021-11-12 |  | 2021-11-12
Provisioning Ancillary Services from Cloud (TBD)
Provisioning Watson Services (NLC/NLU)
Provisioning FaaS
Provisioning WDS
Installing EFK
| Add worker node for EFK |  |  |  | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12
| Install EFK |  |  |  | 2021-11-12 | 2021-11-12 | 2021-11-15 | 2021-11-12
| Add RBAC and Test EFK |  |  |  | 2021-11-16 |  | 2021-11-17
Configuring Firewall
| Apply Rule on Vyatta |  |  |  | 2021-10-29
Testing Vyatta
Installing Prometheus Stack
| Install Grafana |  |  |  | 2021-11-13 | 2021-11-13 | 2021-11-13 | 2021-11-13
| Connect ROKS's default Prometheus to Grafana |  |  |  | 2021-11-13 | 2021-11-13 | 2021-11-13 | 2021-11-13
| Configure AlertManager |  |  |  | 2021-11-13 | 2021-11-15 | 2021-11-15 | 2021-11-15
| Test end to end |  |  |  | 2021-11-15 | 2021-11-15 | 2021-11-16
Install Service Mesh
| Install Elasticsearch |  |  |  | 2021-11-15 | 2021-11-15 | 2021-11-19
| Install Jaeger |  |  |  | 2021-11-15 | 2021-11-15 | 2021-11-19
| Install Kiali |  |  |  | 2021-11-15 |  | 2021-11-22
| Install Service Mesh |  |  |  | 2021-11-15 |  | 2021-11-22
| Test Service Mesh |  |  |  | 2021-11-16 |  | 2021-11-22
Deploy Solutions Through Pipelines
(One Test Soln will be configure to deploy in UAT) | Configure Stage in Pipeline for UAT |  | SRE / Soln Team |  | 2021-11-22 |  | 2021-11-22
(Same Test Soln will be tested in UAT) | Deploy Soln in UAT |  | SRE / Soln Team |  | 2021-11-22 |  | 2021-11-22
| Test Soln in UAT |  | SRE / Soln Team |  | 2021-11-22 |  | 2021-11-24
Setup Access for Soln Teams
| Setup Developer/Deployer Access |  |  |  | 2021-11-25 |  | 2021-12-10